## Sheet1
Incident ID | Date/Time Reported | Incident Description | Severity | Priority | Status | Reported By | Assigned To | System/Module Affected | Steps to Reproduce | Root Cause | Resolution | Date/Time Resolved | Downtime Duration | Comments
101 | 2024-08-01 09:30 | Server downtime | Critical | P1 | Resolved | John | IT Support | Web Server | Attempt to access the website. | Server overload | Server rebooted and load balanced | 2024-08-01 11:00 | 1.5 hours | Monitored server post-reboot
102 | 2024-08-05 14:15 | Database connection issue | High | P1 | In Progress | Alice | Database Team | Database | Run a query in the database. | Configuration error | Configuration updated |  |  | Pending further investigation
103 | 2024-08-10 18:00 | Slow response time | Medium | P2 | Open | Bob | Network Team | Network | Ping the server from any workstation. | Bandwidth issue | Increased bandwidth allocation